## Sheet1
Sprint | User Stories | Task Owner | Take Help From | Due Date | %Completed | Status
Sprint 2 - 09/02/2018 (Deliver Subject Area, Tables, Columns along with data) | Login Page UI | Sumeet | Saradhi,Anuj | 2018-09-02
| Analysis Page UI - 1 - Folder Structure of Subject Area,Tables and Columns | Anuj | Anuj,Naseer,Ajitesh | 2018-09-02
| Analysis Page UI - 2 - Aligning and design Page (Select Visualization(D3/High Chart) , Select Graph type, placing loggedin user,log off button etc.. | Rinkita | Anuj,Prasad,Richa | 2018-09-02
| Creating visaulization (Steamgraph) in OBIEE | Faraz | Shyam,Ajitesh,Faraz | 2018-09-02
| SA dropdowns- Calling OBIEE webservices,SOAP using and Angular JS | Prasad | Prasad,Faraz | 2018-09-02
| Rendering Steamgraph Visulaization in Analysis Page | Ajitesh | Sumeet and Prasad | 2018-09-02
| HTML/CSS/Bootstrap Place holders for graph Parameters | Richa | Naseer,Ajit | 2018-09-02
| X and Y axis, colors,height,width etc.. Functionality | Saradhi | Richa,Shyam,Sumeet | 2018-09-02
| Advaned XML format of the Visulaization,Calling OBIEE web service & Save visualization | Sumeet | Team | 2018-09-02
| E2E UI adjustments | Naseer | Prasad,Faraz | 2018-09-02
| OBIEE Admin Monitering Stuff | Syam | Prasad,Syam | 2018-09-02